## Sheet1
Retrospective meetings
Sprint | 1
What is working | What needs improvement | Actions to take for next sprint
Pair programming | Delete branches less frequently (sometimes after a merge branch is deleted, even when it is still needed) | Continue to run daily stand ups to allow people to raise issues and update rest of the team
TDD helped ensure all logic needed in the server was present | Communication between groups could be a bit better (eg. after tests for TDD are written, inform the group in charge of dev, as this resulted in half a day or so of lost time) | Ensure with everyone that a branch is no longer active before deleting it
Use of Github project board |  | Create a chat on discord for the project to enable better communication
Daily stand ups
Code reviews
Sprint | 2
What is working | What needs improvement | Actions to take for next sprint
New discord chat for the project, super helpful as allows for quick communication and file transfers | Project board was a bit out of date for first half of sprint (forgot to move sprint 2 tickets into 'to do') | Ensure project board is up to date prior to starting the sprint
Sharing programming problems outside of your pair programming group to the rest of team (eg. when we were getting errors during the writing of the test scripts for the front end, was helpful to reach out to rest of the team and get help and feedback on why) | Time management could be better, found that some tickets took far longer then others. Might be a good idea to allocate points to each ticket, should help with ticket allocation and help us focus more time on higher rated tickets | <-- try adding scores to each ticket
Better use of branches, not deleted as frequently so don't have to remake them | One team-member got coivd during this sprint, impacted speed of sprint quite heavily
Switching partners for pair programming helps provide a different point of view on the problem. Also allows you to work with everyone
Code review comments are informative when code review fails
Sprint | 3
What is working | What needs improvement | Actions to take for next sprint
Manual QA test scripts are well written and test the front end well | UAT testing could not be done due to time constraints | N/A last sprint
Overall satisfied with final product created, happy with how it works, looks and scales | A lot of the third sprint tickets were allocated to one person, on future projects ensure allocation is even